## Communication Plan
Sample Communications Plan
Timing | Date | Purpose/ADKAR | Audience | Message/Content | Communication Vehicle | Sender | Comments/Feedback
Pre-implementation | X/X/20XX | Generate awareness of leadership's support Awareness | All impacted stakeholders | • New Recruiting system coming • Leadership supports the implementation of the new system • Benefits for campus, for staff and for faculty | Face-to-face presentation | Authorizing Sponsor and/or Reinforcing Sponsor
Pre-implementation | X/X/20XX | Generate awareness and understanding of the new system Awareness | All users of the new system/Recruiters | • Overview of Recruiting system • Support for program • Benefits for campus and recruiters • Timeframes for implementation • Your role in implementation, including participation in testing and training | Face-to-face (or virtual) presentation, supported by email | Project Manager/Wave Coordinator
Pre-implementation | X/X/20XX |  | All impacted stakeholders | High-level information about Recruiting: What, Why, Where, Who, When | Website | Website to be announced at one of the two above meetings
Throughout implementation | X/X/20XX | Generate awareness and understanding of the new system Desire | All impacted stakeholders | • Coming soon “teaser” messages • Updates on progress of implementation • Benefits to expect for different user groups • Interesting facts about recruitment at this campus | Newsletter | Communications Lead (part of Campus Change Team)
Early stages of implementation | X/X/2018 | Build motivation to use the new system Desire | Recruiters | • Rationale and benefits (reiterate) • Gather feedback – Benefits and concerns for Recruiters and Hiring Managers • Brainstorm how to address concerns • Share ‘Frequently Asked Questions’ document and discuss other tools and resources that will be available • Agree on key messages for hiring managers | Face-to-face (or virtual) workshop style session | Reinforcing Sponsor (such as HRO/AVP) and Recruiting Lead
Pre User Acceptance Testing | X/X/2018 | Build motivation to use the new system and knowledge of how it works Desire/Knowledge | Recruiters and optionally change champions (ex. some Hiring Managers) | • Invitation to participate in User Acceptance Testing (UAT) • Benefits of participating in UAT • Time investment and dates | Email | Project Manager/Wave Coordinator
Pre Recruiter training | X/X/2018 | Develop skills to use the system effectively Knowledge/Ability | Recruiters | • Invitation to participate in ‘New User Essentials’ training • What to expect • Dates/times | Email/calendar invite | Project Manager/Wave Coordinator
GO LIVE day | X/X/2018 | Advise key users of system GO LIVE Ability | All stakeholders | • GO LIVE date • What this means for you • Accessing more information | Email | Sponsor
Post GO LIVE | X/X/2019 | Reinforce consistent and effective system use Reinforcement | Managers | • What’s working? • What’s not? • Business impact of new system to date | Face-to-face or virtual meeting (rolling agenda item) | Reinforcing Sponsor (such as HRO/AVP) and Recruiting Lead
Note on H7: Lewis, Breauna: any comments or feedback received regarding the message that was sent