## Instructions
Stakeholder Register Instructions
The Stakeholder Register should be used to identify all the stakeholders who are either directly involved with the project, or whose interests will be impacted by the execution of the project. This register should be updated as new information becomes available. It will be an input to the development of a communications plan during project planning, and will be used to guide the management of stakeholder expectations and the distribution of information during project execution.
The Stakeholder Register consists of 2 tabs:
1 - Stakeholder Register Instructions - Refer to the instructions tab for any clarification when completing this template.
2 - Stakeholder Register - Use this tab to identify all the names of your stakeholders. The table below provides a description of what types of information should be included in each of the columns.
Stakeholder Register Log Fields:
Name of Stakeholder | Enter the name of the Stakeholder.
Position in Campus Organization | Enter the position title the Stakeholder holds on campus.
Project Role | Enter the Stakeholder's role in the Recruiting project. (Wave Coordinator, Lead, Subject Matter Expert (SME), Change Lead, Sponsor, Business Owner etc. ).
Stakeholder Group | Enter the Stakeholder Group the Stakeholder is associated with (Recruiter, Hiring Manager, Department Manager) .
Major Requirements | Enter the Stakeholders major requirements (What does the stakeholder require from the Recruiting implementation in terms of information or deliverables?).
Major Expectations | Enter the Stakeholders major expectations (What does the stakeholder expect to gain or lose from the Recruiting implementation?) .
Degree to which Stakeholder is Impacted by Project | Use the dropdown menu to select the degree to which the Stakeholder is impacted by the Recruiting implementation. (High, Medium or Low).
Level of Stakeholder's Influence/Impact on Project Outcomes | Use the dropdown menu to select the degree to which the Stakeholder can influence the outcomes of the Recruiti8ng implementation (High, Medium or Low).
Preferred Method of Communication | Enter the Stakeholder preferred method of communication (Meeting, Email, Phone Call, Status Report).
Frequency | Enter how often the Stakeholder wants to be communicated to.

## Stakeholder Register
Stakeholder Register
WHO | [5 empty] | WHAT |  |  |  | HOW | WHEN
Stakeholder Name | Email Address | Phone Number | Position in Campus Organization | Project Role | Stakeholder Group | Major Requirements | Major Expectations | Degree to which the Stakeholder is impacted | Level of Influence on the project | Preferred method of communication | Frequency
Example: Jane Doe | jane.doe@calstate.edu | 123-456-7890 | HR Manager | Wave Coordinator | Hiring Manager | paperless process | System is user friendly and easy to navigate | High | Very High | weekly status meetings and email | weekly
Ellen Junn | president@csustan.edu | (209)667-3201 | President | Campus Authorizing Sponsor | Sponsor
Kim Greer | kgreer@csustan.edu | (209)667-3203 | Provost, VP Academic Affairs | Campus Authorizing Sponsor | Sponsor/Cabinet
Julie Johnson | jjohnson34@csustan.edu | (209)667-3006 | Sr. AVP HREOC | Campus Authorizing Sponsor | Sponsor/Cabinet
Matt Collins | mcollins@csustan.edu | (209)667-3137 | AVP, Information Technology | Campus Authorizing Sponsor | Sponsor
Jason Myers | jcmyers@csustan.edu | (209)667-3353 | AVP, Faculty Affairs | Campus Reinforcing Sponsor/Change Mgmt Lead/Recruiting Lead/Communications Lead | Sponsor/Faculty Affairs
Rebekah Temple | rtemple@csustan.edu | (209)667-3376 | HR Director | Campus Reinforcing Sponsor/Change Mgmt Lead/Recruiting Lead | Sponsor/Human Resources
Corey Cardoza | ccardoza@csustan.edu | (209)667-3731 | Director, Information & Learning Services | Campus Reinforcing Sponsor/ Campus IT | Sponsor/IT
Marla Clark | mclark9@csustan.edu | (209)667-3630 | Project & Recruitment Analyst | WCPM/SME/Super User | Human Resources
Veronica Taylor | vtaylor@csustan.edu | (209)664-6735 | Recruitment & Employment Mgr | Communications Lead/SME | Human Resources
Kim McField | kmcfield@csustan.edu | (209)667-3648 | HR Training & Operations Specialist | Training Lead/Liaison | Human Resources
Marie Hirschkorn | mhirschkorn@csustan.edu | (209)664-6734 | Technical Analyst | Training Lead//Liaison/Super User/Campus IT/Sercurity & SSO | Faculty Affairs
Wendy Miller | wdmiller@csustan.edu | (209)667-3401 | Faculty Affairs Specialist | SME | Faculty Affairs
Toni Martinez | trmartinez@csustan.edu | (209)667-3028 | Employment Specialist - Faculty | SME | Faculty Affairs
Nancy Moghadas | ngiagou@csustan.edu | (209)667-3027 | Confidential Office Support | SME | Faculty Affairs
Kassidy Liles | kliles@csustan.edu | (209)664-6552 | Administrative Support Coordinator | SME/Super User | Faculty Affairs
Gabby Bughi | gbughi@csustan.edu | (209)667-3373 | Recruitment & Employment Specialist | Tester | Human Resources
Michaela Dole | mdole@csustan.edu | (209)664-6986 | Student Employment Assistant | Tester | Human Resources
Meshell Alcantar | malcantar7@csustan.edu | (209)667-3747 | Class/Comp, Leaves & Benefits Manager | Tester | Classification
Julie Marlow | jcmarlow@csustan.edu | (209)664-6755 | Technical Analyst | Super UserCampus IT/Security & SSO | Human Resources
John Rezendes | jrezendes@csustan.edu | (209)667-3698 | Analyst/Programmer | Campus IT/Web Developer | IT
Steven Teixeira | steixeira@csustan.edu | (209)667-3944 | Operating Systems Analyst | Security & SSO | IT
Kristina Stamper | kstamper@csustan.edu | (209)667-3916 | Director, Communications & Public Affairs | Communications Rep/Web Developer | Web
Mandeep Khaira | mkhaira@csustan.edu | (209)667-3800 | Graphic Designer | Communication Rep/Web Developer | Web
Darrell Haydon | dhaydon@csustan.edu | (209)667-3077 | VP, Business & Finance | Hiring Authority/Approver | Cabinet
Michele Lahti | mlahti@csustan.edu | (209)667-3837 | VP, University Advancement | Hiring Authority/Approver | Cabinet
Gitanjali Kaul | gikaul@csustan.edu | (209)667-3997 | VP, SPEMI | Hiring Authority/Approver | Cabinet
Paz Oliverez | poliverez@csustan.edu |  | Interim VP, Student Affairs | Hiring Authority/Approver | Cabinet
Michelle Legg | mlegg@csustan.edu | (209)667-3653 | Director, Budget Planning & Admin | Hiring Authority/Approver | Budget
Katherine Trent | ktrent@csustan.edu | (209)667-3425 | Senior Budget Analyst | Approver | Budget
Note on F8: Examples: Functions: Recruiters, Hiring Managers... Departments: Academic Affairs User Groups: Applicants

## Sheet2 (hidden)
Degree to which the Stakeholder is impacted
Select one:
High
Medium
Low