## Slide 2
SESSION 1016
DATE OF PRESENTATION
Go live on enrollment: A story of success in PSCS
implementation in YIC colleges in Yanbu
Eng. SAIF Mohammad Alsaif
Vice Dean for Admission & Registration for Admission Affairs
University of Dammam
alsaeef@uod.edu.sa
+966133332702

## Slide 3
    AGENDA
    Consultation Unit at Deanship of Adm. & Regis. at UOD
      CU unit emergence , Geographical scope, Beneficiary and customers.
      Services and Products ,Expertise
    Yanbu Industrial Colleges (YIC )Project History
    Project status when UoD_CU interfered (1st August 2016)
    Plan: One month implementation - Enrollment Module
    Progress and Current status
    Recommendations
    Contact Info

## Slide 4
Unit Emergence :
  The Unit was Established with the consent of the University Council and approved by Ministry of Education
  The geographical scope:
  The unit can provide advisory, Implementation services and studies related to the SIS applications in the Kingdom of Saudi Arabia and the Gulf Cooperation Council (GCC) countries.
  Beneficiary and customers :
  Governmental and private universities
  Government and private colleges
  Training centers & Institutes
  School complexes
Consultation unit in of Adm. & Regis. at UOD

## Slide 5
  Services :
  Consultation for any educational institution PSCS Implementation within the geographical scope.
  Consultation on defining the requirements and specifications for SIS projects.
  Consultation on defining the prober architecture of infrastructure.
  Full Implementation of PSCS project.
  Installation of any of the products mentioned in the Products slide related to SIS.
  Training and supporting clients .
Consultation unit in Deanship of
admission at UOD

## Slide 6: Consultation unit in Deanship of admission at UOD
  Products :
    Full automated Admission system
    Full automated workflows and procedures related to student records through self-service such as:
    Workflow for College Transfer
    Workflow for Major Transfer
    Workflow for Apology/Postpone Applications
    Financial applications (Advance, relief, housing ........... etc.)
    Workflow for Internal Visitor Student
    Graduation Approval Workflow
    Workflow for Rejoin Program Application
    Workflow for Approval of Update in Personal Information

## Slide 7: Consultation unit in Deanship of admission at UOD
  Products : (continue )
    Workflow to Transfer from Distance Learner to Full Time and Vice Versa
    Workflow to request for University Accommodation
    Workflow for Requesting Loan from University
    Workflow for Support Allowance Application
    Workflow for Gift Allowance Application
    Workflow for Transfer Credits for External Transferred Students
    Workflow for Course Exemptions
    Workflow for Transfer Credit for UoD Students Visiting External University.

## Slide 8: Consultation unit in Deanship of admission at UOD
  Expertise :
    The expertise is only related to People Soft Campus Solution (ORACLE product) .
    The consultants, academics, technicians and managerial working in the unit has experience of not less than ten years in academic related jobs and practiced working on SIS applications for more than five years, which qualifies the unit to provide advisory services and studies for the customers with high professionalism and knowledge and experience .

## Slide 9
Kingdom of Saudi Arabia formed the Royal Commission of Jubail and Yanbu in 1975 as two Industrial and petrochemical hub, the Royal Commission established the Yanbu Industrial College in 1989. YIC maintains strong relationships with local industry and the professions to became major sources of manpower.
Number of colleges: 4
Number of campuses: 4
Number of programs: 41
Number of students: 30,000 (10,000 active )
Degrees: 2
    Bachelor degrees
    Associate Diploma
Legacy system: Logsis
    Yanbu Industrial colleges(YIC)
    Project History

## Slide 10
Implementation contract was signed on 27 April, 2013 ( to be completed in 16 months )
The project implementer was diverted to IT management as a client project owner.
IT did not involve the end user (student affairs) in the various stages of the project.
The project went live on Feb , 2014 Which was a failure.
The remedy adopted was to transfer the ownership to the students affairs.
    YIC Project History

## Slide 11
The academic structure was not properly configured in the system
Course catalogue had some mistakes
Repeat rule was not configured
Academic standing was not configured
Program advisements were missing
Departments have been entered as academic groups
No enrollment customizations has been done
    Project status when UoD_CU interfered
    (1st August 2016)

## Slide 12
The client agreed with the contract Implementer to go live with enrolment module and to be implemented by UoD_CU.
This partial project was an emergency rescue of the main project.
The time left for enrollment to be open for students was only one month.
Therefore, the project duration was one month from August 14, 2016 To September 14,2016 Including EID vacation.
Both teams ( UoD_CU and YIC ) were committed to be available 24*7 throughout the project duration.
    Plan: One month implementation
    enrollment module

## Slide 13
Academic structure correction and properly configured (15 Aug to 25 Aug).
Data migration verification (15 Aug to 25 Aug).
Course catalogue corrections (25 Aug to 05 Sep).
Programs advisement were entered (25 Aug to 05 Sep).
The client was verifying all these entries and configurations at every step.
At the end enrollment customizations were done (5 Sep to 10 Sep) .
System was opened for student before enrolment to see there transcript and to give there feedback (10 Sep to 14 Sep) .
Go live on 14 Sep, 2016 for online enrolment
    Outline of the Plan

## Slide 14
System was opened to student to verify their data (10 Sep to 14 Sep) .
The student were provided in their self service with a customized transcript which shows all required data.
Student were providing their comments through Email to their institute.
Comments were tackled by the team in UOD CU and within four days they were over
    Opening the system for student

## Slide 15
Go live on 14 Sep, 2016 for online enrolment a week before classes start.
CU team was getting issues from client team and resolving directly.
Data related issues were few and not major.
Major issues were related to class schedule and time table conflicts
The reason for these conflicts was adopting auto time tabling using a legacy system
The client team were not aware of the logic behind the time table structure which resulted in difficulty in handling block enrollment
The enrollment closed by the end of the second week of the term successfully with 95% of active students enrolled
    Go live for Enrolments

## Slide 16
Scheduled plan
Client to verify all these entries and configurations
Academic structure correction
Data migration verification
Aug 15th
to
Aug 25th
task in parallel
Go
live
Sep14th
Students required to log in the system to check there transcript
Sep 10th
to
Sep 14th
Course catalogue correction
Programs advisement entered
task in parallel
Aug 25th
to
Sep 5th
enrollment customizations
Sep 5th
to
Sep 10th

## Slide 17
For any PS campus solution implementation the owner should be the body in charge of student registration and admission.
IT management should be involved but not as owner.
The client should be in close association with the implementer to assure fulfilling client requirements
Phase implementation in the form of modules is recommended
    Recommendations

## Slide 19
Eng. SAIF Mohammad Alsaif
Vice Dean for Admission & Registration for Admission Affairs
University of Dammam
alsaeef@uod.edu.sa
+966133332702
    Contact Info