## Slide 1: PeopleSoft Campus Solutions Upgrade The Devil in the Details
SESSION 4009
29 Apr 2019

## Slide 2: presenters
Yvonne Yong
Principal IS Analyst
Singapore Management University
yvonneyong@smu.edu.sg
Application Support for Student Information Systems
Over 13 years of experience with PeopleSoft
11 years of experience with Campus Solutions

## Slide 3: Singapore Management University

## Slide 4: Singapore Management University (SMU)
A premier university in Asia, the Singapore Management University (SMU) is internationally recognised for its world-class research and distinguished teaching.
Established in 2000, SMU’s mission is to generate leading-edge research with global impact and produce broad-based, creative and entrepreneurial leaders for the knowledge-based economy.
Home to around 10,000 undergraduate, postgraduate, executive and professional, full- and part-time students.
SMU has six schools: School of Accountancy, Lee Kong Chian School of Business, School of Economics, School of Information Systems, School of Law, and School of Social Sciences.

## Slide 5: SMU & ORACLE

## Slide 6: SMU & Oracle
PeopleSoft Campus Solutions | Version
Current Version | 9.2
Campus Solutions Modules | Admissions & Recruiting Academic Advisement Student Records Student Financials Campus Community Campus Self Service
PeopleTools | Version
Current Version | 8.55

## Slide 7: Content
Project Overview
Project Challenges
Achievements
Concluding Thoughts

## Slide 8: Project overview
Background, Scope
Timeline
Scale & Complexity
Risks
Project Organization

## Slide 9: Project Background & Objectives
The Integrated Student Information System (ISIS) using PeopleSoft Campus Solutions 8.9 had been implemented more than 10 years ago - aged software version was on limited support
Infrastructure was close to end of support life - opportunity to refresh infrastructure to SMU’s preferred platform and reduce maintenance costs
The system upgrade would provide a platform to implement more attractive functions and features in the future

## Slide 10: Project Scope
Technology | Previous | Now
Operating System | Solaris10 | Windows 2012 R2
Database | Oracle 11g | MS SQL 2016
PeopleTools | 8.49 | 8.55
Campus Solutions | 8.9 | 9.2
Retrofit SMU customizations

## Slide 11: Project Timeline
Keep/Drop
SIT
UAT
Performance Security Test
PGP/ Warranty
Initial Pass
Retro-fit1
MTP 2
Retro-fit2
MTP 3
Cut Over
Go Live
Retrofit / Dev
23 Apr 2018
Functional
Technical
30 Nov 2016
23 Apr 2018

## Slide 12: Scale & Complexity
TECHNICAL OVERHAUL
Application
Database
Servers
MANY BUSINESS PROCESSES
> 40K users/year
21 Process Areas
~1000 test cases
OPERATIONAL
IMPACT
Limited downtime
Critical changes during project
INTEGRATION
40 interfacing systems within and external to SMU

## Slide 13: Project RISKs
Limited SMU resources and availability
Underestimated customizations scale and complexity
Concurrent System Changes during Upgrade
Limited Time for Testing

## Slide 14: Strong and Committed Project Team
SMU
Project Steering Committee: Registrar, CFO, CIO
9 Project Management Committee Members
>30 reps from 16 departments/schools
Vendors
2 Project Directors
4 Project Management Committee Members
10 Core Team Members (interviewed by SMU for key roles)
50 technical team members

## Slide 15: Project Challenges
Delays
Software Differences
Change Control
Technical Considerations

## Slide 16: Initial Project Schedule
Tasks were too high-level to predict an accurate master project schedule

## Slide 17: Planned Project Timeline
Keep/Drop
SIT
UAT
Performance Security Test
PGP/ Warranty
Initial Pass
Retro-fit1
MTP 2
Retro-fit2
MTP 3
Cut Over
Go Live
21 Mar 2017
Retrofit / Dev
27 Oct 2017
24 Jan 2018
23 Apr 2018
Functional
Technical

## Slide 18: Actual Project Timeline
Keep/Drop
SIT
UAT
Performance Security Test
PGP/ Warranty
Initial Pass
Retro-fit1
MTP 2
Retro-fit2
MTP 3
Cut Over
Go Live
Retrofit / Dev
27 Apr 2018
5 May 2018
Functional
Technical
MTP 4
Retrofit3
Retrofit4
Fit/Gap

## Slide 19: Causes of Delay
Underestimated extent of customizations
Performance issues took time to resolve
Inadequate SIT scenarios identified
UAT was impacted by SIT delay
UAT had to be phased out by modules based on SIT completion

## Slide 20: Fit Gap Blind Spot
Software version changes underestimated
Different setup data
Translate Values
    Country Table
    Address formats
New fields in delivered pages
Users are unfamiliar and may have impact when used wrongly
Security permissions
New technical features available to irrelevant users
Performance
Maintain Applications
Advisement processing
Student Program/Plan CI
Product Issues
Bugs in Advisement and Enrolment, raised SRs with Oracle Support

## Slide 21: Missed Gap
Example issue due to new field default:
New configuration defaulted as enabled.
Impact: Transactions no longer grouped when posting.
Issue: Automated interface could not process subsequent transaction reversals

## Slide 22: Change Control
Out of more than 200 system changes requested, 25 critical fixes and enhancements could not be deferred to after Go-Live, including:
Tuition Grant requirement for Admissions from MOE
University Admissions Score computations
IRAS requirement for external organisation billing
Enhancements for PDPA policies
Security vulnerability fixes

## Slide 23: System Code Freeze
Code freeze period reduced from 1 year to 2 months
COP1
Initial Pass
Dev
Retrofit1
MTP2
SIT
Retrofit2
COP3
MTP3
UAT
COP Final
Cut Over
PROD
Retrofit3
Retrofit4
COP2
COP4
MTP4

## Slide 24: Environment Planning
Customizations re-application
Development from functional specifications
Oracle to MS SQL Server retrofit
Crystal Reports to XMLP
92
DEV
92
SIT
92
PRD
92
UAT
92
STG
92 DEMO
89
Code Ref
89 DEMO
89
PRD
SIT
Provision after Go-Live
UAT
Performance Testing
Security Vulnerability Testing
Dry Run
Final Cutover

## Slide 25: Actual Environments
Customizations re-application
Development from functional specifications
Oracle to MS SQL Server retrofit
Crystal Reports to XMLP
Critical system bug fixes and enhancements
92
DEV
92
SIT
92
PRD
92
UAT
92
STG
92 DEMO
89
Code Ref
89 DEMO
89
PRD
Final Cutover
Graduation Parallel Run
UAT
(required for UAT with the 40 interfacing systems)
89
Dry Run
89
FV
89
DV
92
DEV2
89
UAT
Performance Testing
Security Vulnerability Testing
(required for concurrent activities)
89
UAT2
92
Dry Run
92
PERF
Dry Run
Report and Data Verification
(required for concurrent activities)
Functional Verification
Data Verification
92
DV
SIT

## Slide 26: Testing
Specific scenarios
Silent issues missed from SIT and UAT scenarios
Datetime handling,
wrong data deletions,
rare scenarios
Performance issues
5 scenarios selected for Performance Testing
Overlooked functions:
Query reports
Batch processes
Infrastructure issues
PRD architecture different from UAT
All file input processes failed
Unsupported filenames
Limited time and resources for testing

## Slide 27: Achievements
Data Intact
Go-Live on Time
Minimal Business Impact

## Slide 28: Data Verification Strategy
Data Reconciliation and Verification Approach
Migrate database
Upgrade Application
Apply Customisations
Functional Data Recon and Verification
Technical Data Recon and Verification
Row Count Recon
Row Count Recon
Comparison by Scripts
Query/ Reports
SQL Extract Compare

## Slide 29: Automate Data Verification
Technical Verification
Prepare scripts to extract data and compare CS89 ad CS92
Discrepancies, if any, will be flagged out
SELECT CS89.EMPLID, CS89.ACAD_CAREER, CS89.INSTITUTION, CS89.STRM, CS89.CLASS_NBR, CS89.CRSE_CAREER, CS89.SESSION_CODE, CS89.SESSN_ENRL_CNTL, CS89.STDNT_ENRL_STATUS, CS89.ENRL_STATUS_REASON, CS89.ENRL_ACTION_LAST, CS89.ENRL_ACTN_RSN_LAST, CS89.ENRL_ACTN_PRC_LAST, CS89.STATUS_DT, CS89.ENRL_ADD_DT, CS89.ENRL_DROP_DT, CS89.UNT_TAKEN, CS89.UNT_PRGRSS, CS89.UNT_PRGRSS_FA, CS89.UNT_BILLING, CS89.CRSE_COUNT, CS89.GRADING_BASIS_ENRL, CS89.GRADING_BASIS_DT, CS89.OVRD_GRADING_BASIS, CS89.CRSE_GRADE_OFF, CS89.CRSE_GRADE_INPUT, CS89.GRADE_DT, CS89.REPEAT_CODE, CS89.REPEAT_DT from cs89.PS_STDNT_ENRL
EXCEPT
SELECT CS92.EMPLID, CS92.ACAD_CAREER, CS92.INSTITUTION, CS92.STRM, CS92.CLASS_NBR, CS92.CRSE_CAREER, CS92.SESSION_CODE, CS92.SESSN_ENRL_CNTL, CS92.STDNT_ENRL_STATUS, CS92.ENRL_STATUS_REASON, CS92.ENRL_ACTION_LAST, CS92.ENRL_ACTN_RSN_LAST, CS92.ENRL_ACTN_PRC_LAST, CS92.STATUS_DT, CS92.ENRL_ADD_DT, CS92.ENRL_DROP_DT, CS92.UNT_TAKEN, CS92.UNT_PRGRSS, CS92.UNT_PRGRSS_FA, CS92.UNT_BILLING, CS92.CRSE_COUNT, CS92.GRADING_BASIS_ENRL, CS92.GRADING_BASIS_DT, CS92.OVRD_GRADING_BASIS, CS92.CRSE_GRADE_OFF, CS92.CRSE_GRADE_INPUT, CS92.GRADE_DT, CS92.REPEAT_CODE, CS92.REPEAT_DT from CS92.PS_STDNT_ENRL
Issues were found from this, leading to fixes in database migration and upgrade scripts

## Slide 30: User Verification
More comprehensive than page sampling and eyeballing operational reports

## Slide 31: Go-Live
Keep/Drop
SIT
UAT
Performance Security Test
PGP/ Warranty
Initial Pass
Retro-fit1
MTP 2
Retro-fit2
MTP 3
Cut Over
Go Live
Retrofit / Dev
5 May 2018
Functional
Technical
MTP 4
Retrofit3
Retrofit4
Fit/Gap

## Slide 32: Resource Levelling
Despite additional activities:
Internal SIT by SMU
Detailed UAT Script Review
Regression Testing
Data Verification UAT
Delta Migration UAT
UAT phase was planned with more than 200 tasks defined with estimated efforts based on test cases, phased based on SIT completion, with detailed resource loading and levelling.

## Slide 33: Cutover Period
Cutover period reduced from 3 weeks to 8 days.
Initial Pass
Move To Production 2
Move To Production 3
Move To Production 4
Dry Run
Final Cutover
4 months
6 days for upgrade
+
2 days for verification and delta migration
Prep
Prep

## Slide 34: Business Operations During Cutover
ISIS - Academic Advisement | ISIS - Interfaces
ISIS - Academic Structure & Calendar | ISIS - Internship & Community Service
ISIS - Admissions | ISIS - Library Course Pack
ISIS - Awards & Special GPA | ISIS - Matriculation
ISIS - Career & Program Records | ISIS - Milestones & Candidature Period
ISIS - Class Schedule & Enrolment (including BOSS) | ISIS - Outgoing Exchange
ISIS - Course Catalogue | ISIS - PeopleTools
ISIS - Examinations | ISIS - Statutory & Statistical Reports
ISIS - Financial Aid | ISIS - Student Biographical Records
ISIS - Graduation and Completion | ISIS - Student Financials
ISIS - Incoming Exchange | ISIS - Student Profiling & Admin Holds
 | ISIS - Transfer Credits & Exemptions
Go-Live period was heavily deliberated to avoid majority of business cycles.
However, it still coincided with the peak periods for postgraduate application submissions, and Undergraduate admissions interview and evaluation.

## Slide 35: Careful Cutover Considerations
CS8.9 (limited transactions)
CS9.2
27 Apr 6pm
Applicant
Staff
CS8.9 (limited transactions)
CS9.2
Downtime
Downtime
Downtime
5 May 9pm
Cut Over
28 Apr 9am
4 May 6pm
Go Live
Migrate Delta

## Slide 36: Concluding Thoughts
Key Learning Points
Project Benefits

## Slide 37: Key Learning Points
Scrutinize the proposed project schedule, tasks and effort
Set detailed expectations and ensure proper quality control and governance from the start of project
Be as detailed as possible early in the project, to identify required tasks, gaps and issues early
Consider opportunities to automate tasks, eg. testing and data verification
Do not take anything for granted

## Slide 38: Project Benefits
New software version on full support
Reduced maintenance costs
Support team acquired new and updated skills
Leveraged new delivered features to replace aged bolt-ons e.g.
  Interactive Advisement Report
  Process Milestones
  Process and Mass Release Service Indicators
Potential to improve business processes e.g. Research Tracking
Potential to implement attractive features, e.g.
  Fluid UI
  Drill-down queries
  Work Centres

## Slide 39: Q&A

## Slide 40: presenters
Yvonne Yong
Principal IS Analyst
Singapore Management University
yvonneyong@smu.edu.sg
all Alliance presentations will be available for download from the Conference Site

## Slide 41: THANK YOU!